## Gantt Chart
GANTT CHART PICARD | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | The Picard |  |  |  |  | COMPANY NAME | [6 empty] | West Virginia Univesity
PROJECT MANAGER |  | Dr. Devine | [11 empty] | 2023-04-24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Create Frontend GUI
1.1 | Create User Interface | Travis Mueller | 2023-08-16 | 2023-08-30 | 2 | 0% | bar: WEEK 1 W to WEEK 3 F
1.1.1 | Peer Code Review | Zack Wildasin | 2023-08-16 | 2023-08-30 | 2 | 0% | bar: WEEK 2 W to WEEK 3 F
1.2 | Testing UI | Travis Mueller | 2023-08-23 | 2023-09-08 | 1 | 0% | bar: WEEK 2 W to WEEK 3 F
2 | Harden Server
2.1 | Implement OpenSCAP | Abdalrahman Afifi | 2023-08-16 | 2023-08-30 | 2 | 0% | bar: WEEK 2 W to WEEK 5 F
2.2 | Test OpenSCAP | Hunter Lavender | 2023-08-30 | 2023-09-08 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 6 F
2.3 | WVUIT Review | Abdalrahman Afifi | 2023-09-08 | 2023-09-15 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 6 F
2.4 | Final Security Implementation | Hunter Lavender | 2023-09-15 | 2023-09-22 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 F to WEEK 8 F
3 | Create the Backend
3.1 | Implement Tables | Abdalrahman Afifi | 2023-09-22 | 2023-10-06 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 7 F to WEEK 9 F
3.2 | Insert Data | Hunter Lavender | 2023-09-22 | 2023-10-06 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 7 F to WEEK 9 F
3.3 | Peer Review | Abdalrahman Afifi | 2023-10-06 | 2023-10-13 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 9 F to WEEK 11 F
3.4 | Test Database | Hunter Lavender | 2023-10-13 | 2023-10-20 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 10 F to WEEK 11 F
4 | Automate Hardening of Each Node
4.1 | Implement Security Requirements for Node Creation | Abdalrahman Afifi | 2023-10-20 | 2023-11-03 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 9 F to WEEK 11 F
4.2 | Peer Review of Configurations | Hunter Lavender | 2023-10-20 | 2023-11-03 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 9 F to WEEK 11 F
4.3 | WVUIT Review | Abdalrahman Afifi | 2023-11-03 | 2023-11-10 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 11 M to WEEK 12 F
4.4 | Final Security Implementation | Hunter Lavender | 2023-11-10 | 2023-11-17 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 11 M to WEEK 12 F
5 | Test Each Algorithm
5.1 | Test Specific Parameters for Each Algorithim | Everyone | 2023-11-17 | 2023-12-08 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 11 M to WEEK 12 F
5.2 | Test Output for Each Algorithim | Everyone | 2023-11-17 | 2023-12-08 | 2 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 11 M to WEEK 12 F
5.3 | Bug Fixes | Everyone | 2023-11-17 | 2023-12-08 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 11 M to WEEK 12 F